## Sheet1
Task | Start Date | End Date | No. Days To Complete | Action
1 | 2019-11-25 | 2019-12-09 | 14 | Begin Implementation of Mobile Application
2 | 2019-12-03 | 2019-12-04 | 1 | User Requirements Gathering
3 | 2019-12-04 | 2019-12-05 | 1 | Revise User Requirements
4 | 2019-12-09 | 2019-12-23 | 14 | Begin Implementation of Web-Portal
5 | 2019-12-16 | 2019-12-30 | 14 | Begin Implementation of Controller
6 | 2019-12-23 | 2019-12-06 | 14 | Begin Implementation of Model
7 | 2020-01-06 | 2020-01-10 | 4 | Integrate Components
8 | 2020-01-10 | 2020-01-24 | 14 | Debug
9 | 2020-01-24 | 2020-01-29 | 5 | Test in 1st Usability Evaluation
10 | 2020-01-29 | 2020-01-31 | 2 | Prepare Results from 1st Usability Evaluation
11 | 2020-01-31 | 2020-02-01 | 1 | Evaluate Results of 1st Usability Evaluation
12 | 2020-02-01 | 2020-02-06 | 5 | Implement Appropriate Changes From 1st Usability Evaluation Results
13 | 2020-02-06 | 2020-02-07 | 1 | Write Automated Tests
14 | 2020-02-07 | 2020-02-08 | 1 | Implement Analytics into App
15 | 2020-02-08 | 2020-02-09 | 1 | Write Google Form for 2nd Usability Evaluation
16 | 2020-02-09 | 2020-02-11 | 2 | Launch App in Public Beta for 2nd Usability Evaluation
17 | 2020-02-11 | 2020-02-12 | 1 | Promote 2nd Usability Evaluation
18 | 2020-02-12 | 2020-02-22 | 10 | Receive Responses To 2nd Usability Evaluation
19 | 2020-02-22 | 2020-02-23 | 1 | Evaluate Results of 2nd Usability Evaluation
20 | 2020-02-23 | 2020-02-28 | 5 | Implement Appropriate Changes From 2nd Usability Evaluation Results
21 | 2020-02-28 | 2020-03-01 | 1 | Verify Compliance with Apple App Store and Google Play Store
22 | 2020-03-01 | 2020-03-02 | 1 | Deploy Application and Web-Based Portal
Dissertation Submission Deadline: |  |  |  | 2020-04-21